## Card
Project Name
Project Leader
Project's Steering Committee
Project type
Start Date
Status
Last Modification/Update
Project scope: Production/Machinery/Product/Sales etc.
Out of scope (what is not part of the project)
Project Reason and Goal (business need; benefit and value of the project)
Measureable targets (f.ex. KPIs, std t, etc. before and after):
Project time frame (start & anticipated finish):
Success Criteria (proof that project delivered expected benefits)
Risk analysis
Change register in scope, budget, success criteria etc. approved by steering committee)

## Zadania
Project:
Start date:
Update by:
Update on:
* nie wszystkie zadania z listy muszą być umieszczone w harmonogramie, zależy to od wdrożenia, do listy można dodawać nowe zadania.
WBS ID. | Action / Description
General
A1 | Contract review
A2 | PUA (podpisnie cennika)
A3 | Official PDOC + labels
A4 | Forecast (Supply info)
A5 | Process flow aproval by IKEA
A6 | batch "-1" control & approval
A7 | "zero batch" control & approval (internal HAP) FBP
A8 | Gate check control & approval (internal HAP)
A9 | First Delivery Inspection control & approval HAP
A10 | Sale start in IKEA (SSD)
Quality
B1 | Tests TVOC/FR
B2 | Mobelfacta test result
B3 | FMEA analize
B4 | Special processes procedure
B5 | Documents connection in CONNECT
B6 | Mobelfacta wewnętrzna HAP
Calculations
C1 | BOO i BOM
C2 | Structures in Movex (+warehouse Z99)
C3 | Price calculation based on Matrix volumes
Implementation
D1 | PDOC validation & confirmation
D2 | PDOC confirmation by IKEA Technician
D3 | Create process flow
D4 | Production tests
D5 | Production instruction preparation (SOP)
D6 | Production instruction edition
D7 | Production workers traning
D8 | Preliminary DWP
D9 | Final DWP (IKEA system)
D10 | Proces specjalny klejenia
Spring production
E1 | Produkcja sprężyn na testy Mobelfacta
E2 | Przygotowanie karty surowca dla nowych surowców
Planning
F1 | System settings - planning
F2 | Sales settings
F3 | Saftey stock set up
Production
G1 | Production start
G2 | FG safety stock ready
Purchasing
H1 | New raw materials list
H2 | Order RM for tests & zero batch
H3 | Collect certificates, etc for new RM
H4 | Order RM to secure production start up
Warehouse / Logistic
I1 | Warehouse map actualization for FG
I2 | Warehouse map actualization for RM
I3 | System settings - warehouse
I4 | Logistic settings
I5 | Start dispatch to IKEA
I6 | wysyłka materacy do IKEA

## Harmonogram przykład
G03_P01_I01_Z02v1 |  |  |  | 2024-07-22
Harmonogram Projektu (Project schedule) | [12 empty] | Wykres Gantta (Gantt chart)
ID | Zadanie / Opis (Action / Description) | Termin (Deadline) | Długość (Lenght) [dni] | Odpowiedzialny (Responsible) | Status | Termin wykonania | Komentarz (Comments) | 2020
[8 empty] | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 21 |  |  |  |  | Week 22 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32 |  |  |  |  | Week 33 |  |  |  |  | Week 34 |  |  |  |  | Week 35 |  |  |  |  | Week 36 |  |  |  |  | Week 37 |  |  |  |  | Week 38 |  |  |  |  | Week 39 |  |  |  |  | Week 40 |  |  |  |  | Week 41 |  |  |  |  | Week 42 |  |  |  |  | Week 43 |  |  |  |  | Week 44 |  |  |  |  | Week 45 |  |  |  |  | Week 46 |  |  |  |  | Week 47 |  |  |  |  | Week 48 |  |  |  |  | Week 49 |  |  |  |  | Week 50 |  |  |  |  | Week 51 |  |  |  |  | Week 52 |  |  |  |  | Week 53 |  |  |  |  | Week 54 |  |  |  |  | Week 55 |  |  |  |  | Week 56 |  |  |  |  | Week 57 |  |  |  |  | Week 58 |  |  |  |  | Week 59 |  |  |  |  | Week 60 |  |  |  |  | Week 61 |  |  |  |  | Week 62 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 23 |  |  |  |  | Week 24 |  |  |  |  | Week 25 |  |  |  |  | Week 26 |  |  |  |  | Week 27 |  |  |  |  | Week 28 |  |  |  |  | Week 29 |  |  |  |  | Week 30 |  |  |  |  | Week 31 |  |  |  |  | Week 32 |  |  |  |  | Week 33 |  |  |  |  | Week 34 |  |  |  |  | Week 35 |  |  |  |  | Week 36 |  |  |  |  | Week 37 |  |  |  |  | Week 38 |  |  |  |  | Week 39 |  |  |  |  | Week 40 |  |  |  |  | Week 41 |  |  |  |  | Week 42 |  |  |  |  | Week 43 |  |  |  |  | Week 44 |  |  |  |  | Week 45 |  |  |  |  | Week 46 |  |  |  |  | Week 47 |  |  |  |  | Week 48 |  |  |  |  | Week 49 |  |  |  |  | Week 50 |  |  |  |  | Week 51 |  |  |  |  | Week 52 |  |  |  |  | Week 53 |  |  |  |  | Week 54 |  |  |  |  | Week 55 |  |  |  |  | Week 56 |  |  |  |  | Week 57 |  |  |  |  | Week 58 |  |  |  |  | Week 59 |  |  |  |  | Week 60 |  |  |  |  | Week 61 |  |  |  |  | Week 62 |  |  |  |  | Week 32 |  |  |  |  | Week 33 |  |  |  |  | Week 34 |  |  |  |  | Week 35 |  |  |  |  | Week 36 |  |  |  |  | Week 37 |  |  |  |  | Week 38 |  |  |  |  | Week 39 |  |  |  |  | Week 40 |  |  |  |  | Week 41 |  |  |  |  | Week 42
[8 empty] | 2 | 3 | 4 | 5 | 6 | 9 | 10 | 11 | 12 | 13 | 16 | 17 | 18 | 19 | 20 | 23 | 24 | 25 | 26 | 27 | 30 | 31 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 28 | 29 | [200 empty] | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15
[8 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
A1 | Contract review
A2 | PUA (podpisnie cennika)
A3 | Official PDOC + labels
A4 | Forecast (Supply info)
E1 | Produkcja sprężyn na testy Mobelfacta
E2 | Przygotowanie karty surowca dla nowych surowców
H1 | New raw materials list
H2 | Order RM for tests & zero batch
MILLESTONE 1 | Podpisany kontrakt z IKEA
MILLESTONE 2 | Wyprodukowana sprężyna
D1 | PDOC validation & confirmation
D2 | PDOC confirmation by IKEA Technician
C1 | BOO i BOM
C2 | Structures in Movex (+warehouse Z99)
C3 | Price calculation based on Matrix volumes
D5 | Production instruction preparation (SOP)
D4 | Production tests
MILLESTONE 3 | Wyprodukowana sztuka materaca
F1 | System settings - planning
F2 | Sales settings
F3 | Saftey stock set up
A5 | Process flow aproval by IKEA
H4 | Order RM to secure production start up
I1 | Warehouse map actualization for FG
I2 | Warehouse map actualization for RM
I3 | System settings - warehouse
H3 | Collect certificates, etc for new RM
B3 | FMEA analize
D4 | Production -1
I4 | Logistic settings
D8 | Preliminary DWP
B5 | Documents connection in CONNECT
B1 | Tests TVOC/FR
B2 | Mobelfacta test result
A6 | batch "-1" control & approval
MILLESTONE 4 | Testy zewnętrzne
.
D6 | Production instruction edition
D7 | Production workers traning
D9 | Final DWP (IKEA system)
A7 | "zero batch" control & approval (internal HAP) FBP
A8 | Gate check control & approval (internal HAP)
G1 | Production start
G2 | FG safety stock ready
A9 | First Delivery Inspection control & approval HAP
I5 | Start dispatch to IKEA
A10 | Sale start in IKEA (SSD)
MILLESTONE 5 | Wynik Go na raporcie FBI
MILLESTONE 6 | Wynik Go na raporcie Gate Check
MILLESTONE 7 | Wynik Go na raporcie FDI
|  | Legenda: |  | 0 | 0 |  | Plan/ nie wystartowane
|  | (Legend:) |  | 1 | 1 |  | Wg planu
|  |  |  | 2 | 2 |  | Opóźnione
|  |  |  | 3 | 3 |  | Opóźnione i Krytyczne
|  |  |  | 4 | 4 |  | Wykonane

## Kamienie milowe
Numer | Opis | Termin (Deadline) | Status
MILLESTONE 1 | Podpisany kontrakt z IKEA
MILLESTONE 2 | Wyprodukowana sprężyna
MILLESTONE 3 | Wyprodukowana sztuka materaca
MILLESTONE 4 | Pozytywny wynik testów zewnętrznych (mobelfakta, TVOC,FT)
MILLESTONE 5 | Wynik Go na raporcie FBI (przeprowadzamy sami w HAP)
MILLESTONE 6 | Wynik Go na raporcie Gate Check
MILLESTONE 7 | Wynik Go na raporcie FDI

## Przed FBP Check list
Before FBP checklist
Wszystkie Działy
plan czasowy (wykres Gantta)
Zarząd
podpisanie Supplier Implementation Request
+ wersja elektroniczna na FBP
Dział Zapewnienia Jakości
Connect
nie póżniej niż 2 tyg. Przed FBP
FMEA
musi być na FBP + wysłać Technikowi nie później niż 5dni przed Gate Checkiem
Dział Techniczny
przygotowanie palety
Grupa A - po 1 palecie z każdego rozmiaru
Grupa B i C - po 1 palecie z największego i najmniejszego rozmiaru
Testy transportowe:
stacking capacity test
transportation test
stability test: 10° i 27°
store handling test
consumer package handling test*
muszą być na FBP + wysłać Technikowi nie później niż 5 dni przed Gate Checkiem
process flow map
DWP
Wszystkie Działy
e-mail zgłaszający gotowość do przeprowadzenia FBP
nie później niż 7 dni przed wcześniej ustalonym terminem
*nie zawsze występuje

## dropdown (hidden)
Plan | Improvement
In progress | Developmental
Done | Strategic
On Hold
Delayed
Rejected